Template for progress report

# Project Title: Strengthening National Capacities for Safeguarding Intangible Cultural Heritage for Sustainable Development in Bangladesh

# Target Country or Region: Bangladesh

# UNESCO Budget code and donor Reference if appropriate: 199GLO4638

# Funding source: Azerbaijan – Earmarked contribution to the Intangible Cultural Heritage Fund

# Total Budget approved: US$ 200,000

# Reporting Period: April 2016 - October 2017

# Executing Agency: UNESCO Dhaka

# Implementing partners: Ministry of Cultural Affairs, Bangladesh Shilpakala Academy

# Project starting date: April 2016

# Project completion date: March 2018

# Responsible Sector: Culture

# Name of Person completing Report: Kizzy Tahnin

This progress report presents the main findings of a self-evaluation exercise conducted by the responsible UNESCO project officer(s) and covers the following:

- Summary and Background

- Description of project implementation for the period under review

- Progress towards results

- Sustainability

- Workplan

- Visibility

- Challenges and lessons learnt and modifications to the project

- Annexes

- Summary and Background

Bangladesh has a rich tradition in cultural heritage, specifically intangible cultural heritage. However, the more recent history and developments have affected and increasingly threaten these practices and traditions. Stemming from this realization, the Bangladesh Government has addressed this issue and participated in the UNESCO programme for the Masterpieces of the Oral and Intangible Cultural Heritage – getting one tradition proclaimed as Masterpiece in the process (Baul Songs). In addition, in 2009 Bangladesh ratified the 2003 UNESCO Convention for the Safeguarding of the Intangible Cultural Heritage, thereby demonstrating its commitment to establish mechanisms for the promotion and protection of ICH in the country. Recent developments include the inscription of Traditional art of Jamdani weaving in 2013 and Mongol Shobhajatra in 2016 on the Representative List of the Intangible Cultural Heritage of Humanity.

The intense social changes, globalization, urbanisation and economic development are increasingly affecting the traditional lifestyle of Bangladesh. To safeguard Bangladeshi intangible heritage despite the rapidly changing societal organization from which many traditions originate, and as highlighted in the national workshop on the Implementation of the 2003 Convention for the Safeguarding of the Intangible Cultural Heritage held in 2013, the Bangladesh Government has identified that an appropriate inventorying system needs to be established. Furthermore, despite having successfully included one element to the Representative List in 2013, a nomination failed in 2014 and another had been referred in 2015 highlighting the need for a more comprehensive understanding by relevant entities and stakeholders to enhance the overall quality of nomination files in order to reach international standards and contribute to the safeguarding of Bangladesh’s intangible heritage.

Finally, government authorities, relevant stakeholders and practitioners have acknowledged that the various issues, modalities and implications of the 2003 Convention need to be strengthened and better understood and capacity-building is necessary to assist Bangladesh authorities and relevant stakeholders.

The activities implemented within the framework of this project aim:

Main Objective:

To strengthen the capacities of Bangladesh to safeguard its intangible cultural heritage through effective implementation of the Convention for the Safeguarding of the Intangible Cultural Heritage

Specific Objectives:

- To enhance the understanding of the national authorities of the obligations entailed by the ratification of the UNESCO Convention and its implementation

- To build up a critical mass of national capacity so that Bangladesh will have a sustainable framework for safeguarding intangible heritage and implementing the Convention

- To develop an inventory for ICH at the national level

- To sensitize national authorities about the importance and significance of safeguarding intangible cultural heritage, and in particular ICH elements in need of urgent safeguarding, by providing some consultative guidance and advisory on ICH Policy development; and by reinforcing their capacities to prepare nomination files for inscription on the Lists of Intangible Cultural Heritage.

- Description of project implementation for the period under review

Activities Undertaken:

At the onset of the project, Ministry of Cultural Affairs, nominated Bangladesh Shilpakala Academy as a responsible organization and implementing partner of this project and future activities on ICH safeguarding.

Bangladesh Shilpakala Academy in cooperation with UNESCO Dhaka, reviews and identifies any required need for adjustment or improvement of interventions and follow-up.

Two international experts were identified and selected by UNESCO in cooperation with Bangladesh Shilpakala Academy and conducted two trainings: on implementing the Convention at the national level (IMP) and on community-based inventorying (INV).

Outputs Generated:

|  | Activity | Description | Output |
| --- | --- | --- | --- |
| 1. | Sharing and dissemination of the project to the relevant stakeholders | The objectives and activities of the project was disseminated and shared to relevant partners through various consultative and discussion meetings. | Brochure on the project |
| 2. | Capacity-building training on the Implementation of the 2003 Convention at the national level | This training focused on the improvement of national capacities on the implementation of the 2003 Convention. The workshop identified the key areas for guidance and capacity enhancement in the context of implementation of the Convention with particular focus on enhancement of ICH safeguarding measures. | Trained stakeholders: 25 Female: 5 Male: 20 Workshop materials provided Action plan generated from the workshop by the participants |
| 3. | Capacity-building training on community-based inventorying | This training focused on the inventorying of ICH elements in Bangladesh. The workshop identified next steps of action in the preparation and development of a Bangladesh ICH inventorying system. | Trained stakeholders: 26 Female: 4 Male: 21 Workshop materials provided Action plan generated from the workshop by the participants |

Problems encountered in project delivery and corrective actions taken:

- Delayed project start by almost one year due to the required reviewing and approval process of Government;

- Delay in project progress - start of training activities - due to restricted availability of the 2 international trainers

- Staff changes in the dedicated ministries of relevant government officials

- Availability of the same participants in all the trainings

- Progress towards results

Summary Table

| Overall goal of the project: To strengthen the capacities of Bangladesh to safeguard its intangible cultural heritage through effective implementation of the Convention for the Safeguarding of the Intangible Cultural Heritage | Overall assessment : |
| --- | --- |
| Expected Results | Performance Indicators (PI) and associated Target (T)/baselines (b) | Achievement(s) | Outputs/deliverables contributing to expected results |
|  | Programmed | Attained |  |  |
| Title of Expected Result N° 1 Bangladesh authorities learned how to meet their national obligations under the Convention | PI: Capacity building training on the Implementation of the 2003 Convention at the national level T/b: 1 training/ workshop on the implementation of the Convention in Bangladesh in 2013 | Capacity building training on the Implementation of the 2003 Convention at the national level completed successfully | The workshop enhanced the understanding of the national authorities about the obligations entailed by the ratification of the UNESCO 2003 Convention and its implementation. Also, the workshop identified key areas for guidance and capacity enhancement in the context of implementation of the Convention with particular focus on enhancement of ICH safeguarding measures. | Output/deliverable 1: Trained stakeholders: 25 Female: 5 Male: 20 Training Workbook Relevant materials translated in Bengali Brochure on the Project Action plan generated from the workshop by the participants |
|  | PI: T/b: |  |  | Output/deliverable 2: |
| Title of Expected Result N° 2 Communities and custodians learned how to inventory, document and protect their ICH in cooperation with officials of relevant governmental institutions and non-profit organizations | PI: Capacity-building training on community-based inventorying T/b: 1 training/ 0 baseline | This workshop f on the inventorying of ICH elements in Bangladesh completed successfully. | The workshop sensitized the participants about the need and mechanism on developing pilot ICH Inventorying in Bangladesh for the sake of ICH safeguarding. Also, the workshop identified next steps of action in the preparation and development of a Bangladesh ICH inventorying system. The experts and UNESCO Dhaka worked closely to ensure presence of community level participants and maximum impact on developing pilot ICH inventorying in Bangladesh. . | Output/deliverable 1: Trained stakeholders: 26 Female: 4 Male: 21 Training Workbook Relevant materials translated in Bengali Action plan generated from the workshop by the participants |
|  | PI: T/b: |  |  | Ouput/deliverable 2: |

- Sustainability

- The capacity building workshops created a better cooperation between the relevant authorities such as: government authorities, academia, community, NGOs and UNESCO to safeguard and promote ICH of Bangladesh

- Bangladesh Shilpakala Academy has been reinforced as responsible organization for safeguarding intangible cultural heritage in Bangladesh, demonstrated through establishment of an ICH committee under the chairmanship of Shilpakala Academy

- Bangladesh Shilpakala Academy ensured its support and lead activities related to safeguarding and promotion of intangible cultural heritage in Bangladesh

- Participants ensured their institutional support in safeguarding and promoting ICH in Bangladesh

- Bangladesh national authorities as well as project partners have recognized the success of this approach of safeguarding ICH and the needs of ICH inventorying and are keen in further partnership with UNESCO in scaling up this approach.

## Workplan

| Sl. | Activity | Original Time-plan | Revised Time-Plan |
| --- | --- | --- | --- |
| 1. | Capacity-building training on the Implementation of the 2003 Convention at the national level | August 2016 | January 2017 |
| 2. | Capacity-building training on community-based inventorying | October 2016 | September 2017 |
| 3. | Development of ICH pilot inventory | Oct 2016 -Oct 2017 | November 2017- August 2018 |
| 4. | Capacity-building workshop on elaborating nominations to the Lists | May 2017 | May 2018 |
| 5. | Consultation on ICH policies, legislation and institutional infrastructure | August 2016 | May 2018 |
| 6. | Follow up and evaluation | November 2017 – March 2018 | August-September 2018 |

- Visibility

- Project brochure produced and disseminated to relevant stakeholders

- Project outputs and key events prominently featured on UNESCO Dhaka's website

- Action plans generated from two workshops, disseminated to relevant stakeholders

- The donor is being acknowledged in all printed and online documents

- The project activities and outcomes are being published on UNESCO website

- Challenges, lessons learnt and modifications to the approved project

To attain the overall goal of the project, UNESCO Dhaka Office strategically emphasises on strengthening capacities of national stakeholders and to create a platform for them through the two workshops on implementation and nomination, to meet their obligations for safeguarding intangible cultural heritage as outlined in the 2003 Convention.

Due to the lengthy reviewing and approval, process of Government, the project started late. However, during the project, especially after the completion of the two workshops the understanding of the national entities on the implementation of the ICH Convention and implementation has been strengthened. Communication gap between national authority with non-governmental entities, academia and community representatives needs to be minimized further.

Due to the unforeseen delayed project start by almost one year as the government authorities required a thorough reviewing and approval process; and a further unforeseen delay in project progress - start of workshops - due to lengthy identification / availability of the 2 international trainers due also to government authorities involvement in this process, time was lost.

To achieve the best outcomes of the project, especially to provide required time for the implementation of the inventorying activity, a no-cost extension of the project period is required. From previous end date March 2018 to new end date September 2018, as outlined in below table:

| Activity | Original Time-plan | Revised Time-Plan |
| --- | --- | --- |
| Capacity-building training on the Implementation of the 2003 Convention at the national level | August 2016 | January 2017 |
| Capacity-building training on community-based inventorying | October 2016 | September 2017 |
| Development of ICH pilot inventory | Oct 2016 -Oct 2017 | November 2017- August 2018 |
| Capacity-building workshop on elaborating nominations to the Lists | May 2017 | May 2018 |
| Consultation on ICH policies, legislation and institutional infrastructure | August 2016 | May 2018 |
| Follow up and evaluation | November 2017 – March 2018 | August-September 2018 |

- Annexes

    - List of publications, evaluation reports and other outputs/deliverables, when applicable

- Brochure on UNESCO Project for Strengthening National Capacities for Safeguarding Intangible Cultural Heritage for Sustainable Development in Bangladesh